## Slide 1: El Capitan Pilot Operation Time-Line
Engineered and built the fine grinding Hyper-Concentration device
Delivered the device from China to Arizona, customizing it for US
Developed and perfected the recovery process for El Capitan ore
Argon smelted the hyper-concentrates to produce metal ingots
Refined the ingots to recover the precious metals

## Slide 2
The first Recovery of precious metals was accomplished mid-year of calendar 2017. A fine grinding device built in China and shipped to Phoenix was modified to run on US power and enhanced to significantly improve the separation of the precious metals from the concentrates.
What followed in an exceptionally short period of time (2 months) was proof of the ability to produce a hyper-concentrated material ready for smelting and refining.
This process was the first successful recovery of precious metals, beyond assays, from the El Capitan ore. It has been successfully repeated with increasing larger quantities of concentrates. The December 2017 sale of 2,000+ pounds of concentrates completes the Pilot Program, producing precious metals in commercial quantities and value.
After 20 Years – Precious Metals Recovery

## Slide 3
2017
Sep
Oct
Nov
Dec
2017
Feb
Mar
Apr
May
Jun
Jul
9/1/2016
Fine Grinding Device Built in China
11/1/2016
12/1/2016
Test Fine Grinding Device with El Capitan Ore
12/31/2016
1/1/2017
4/15/2017
Ship Fine Grinding Device from China to Phoenix
4/15/2017
Modify Power and Install Hyper-Concentration Mechinism In Phoenix
6/1/2017
6/1/2017
Hyper Concentrate Tucson concentrates (Test runs)
7/1/2017
7/10/2017
Utilize Vacuum Furnace to smelt Hyper-Concentrated Ore
7/15/2017
7/16/2017
Deliver First Ingot to Sipi
7/20/2017
Precious Metals
Pilot Project
Building the System through delivery of the First Ingot for Refining
2016

## Slide 4
2017
2017
Aug
Sep
Oct
Nov
Dec
8/1/2017 - 8/15/2017
Larger Ingot Demonstration
9/20/2017 - 10/5/2017
Specialized (Coper- Platinum) Ingot Demonstration
10/20/2017 - 12/8/2017
2,000 LBS + of Hyper Concentrâtes Prepared
12/27/2017
Sale of Hyper Concentrates
Pilot Project
Selling Hyper Concentrates for Scaled Up Recovery